## Project Implementation Plan (PIP)

Project: Vaccination Drive in Rural Africa
 Document ID: PIP-VDRA-001
 Version: 1.0
 Date: 11 Jan 2026
 Prepared by: Project Management Unit (PMU)
 Audience: Program, Finance, Logistics, M&E, Partners, Field Teams

### 1) Purpose of this plan

This Project Implementation Plan (PIP) explains how the project will be delivered—step-by-step—so that staff, partners, and stakeholders share the same approach to timelines, roles, quality, reporting, and risk management.

### 2) Project summary

Goal: Increase protection against vaccine-preventable diseases by delivering safe, timely vaccination services to underserved rural communities, with strong cold-chain integrity and reliable reporting.

Implementation window: 01 Feb 2026 – 31 Jul 2026 (6 months)
 Target geography: Rural districts in the selected region (multiple catchment areas)
 Primary delivery model: Fixed-site + outreach + mobile sessions (as needed)

### 3) Objectives and targets (project-level)

Objective 1 — Coverage:

- Achieve ≥90% coverage for eligible target groups in prioritized villages (subject to baseline and microplan).

Objective 2 — Access & Equity:

- Reduce travel/time barriers using outreach/mobile sessions and community engagement.

Objective 3 — Quality & Safety:

- Maintain cold-chain compliance ≥95% (no excursions beyond acceptable ranges without documented corrective action).

- Ensure AEFI monitoring is active in all catchment areas.

Objective 4 — Accountability & Reporting:

- Weekly reporting from all sites; monthly consolidated dashboard; final completion report.

### 4) Scope

In scope

- Microplanning and route planning

- Vaccine & ancillary supply forecasting, procurement coordination, and distribution

- Cold chain readiness (equipment checks, temperature monitoring, contingency)

- Staff training and supervision

- Community engagement and demand generation

- Vaccination service delivery (fixed/outreach/mobile)

- Monitoring & Evaluation, reporting, and audit-ready documentation

Out of scope (unless formally approved)

- Construction of new cold rooms

- Large-scale clinical treatment beyond AEFI referral protocols

- Full national-level policy redesign

### 5) Key stakeholders and roles

Internal

- Project Manager (PM): overall delivery, partner coordination, escalation

- Logistics Lead: cold chain, warehousing, transport, distribution

- Finance Lead: budgets, approvals, payments, compliance

- M&E Officer: indicators, data quality, analysis, reporting

- Safeguarding/Focal Point: community feedback, protection concerns, ethics

External

- Ministry/Local Health Authority: authorization, integration with routine services, data alignment

- Health Facilities: service delivery points, storage, staff

- Community Leaders & CHWs: mobilization, mapping, rumor management

- Implementing Partners: field delivery support, outreach teams

### 6) Implementation approach (how delivery will work)

- Readiness phase: confirm target areas, staffing, cold chain, supplies, and microplans

- Pilot / launch: start with a limited set of sites to validate workflows and reporting

- Scale-up: expand to full site list based on readiness and lessons learned

- Optimization: continuous supervision, supportive coaching, targeted outreach for low-coverage pockets

- Close-out: finalize coverage, reconcile stock, complete financial and program reporting, document lessons learned

### 7) Workplan and timeline (high-level)

Phase 1 — Mobilize & Prepare (01–15 Feb 2026)

- Confirm partners, approvals, and operational SOPs

- Recruit/assign teams; finalize duty rosters

- Cold chain assessment + repairs + contingency plan

- Data tools readiness (registers, forms, reporting templates)

Phase 2 — Microplanning & Training (16–28 Feb 2026)

- Village mapping, target estimation, route plans

- Training: vaccination protocol, IPC, AEFI, data reporting, safeguarding

- Dry-run: stock movement simulation + reporting test

Phase 3 — Service Delivery (01 Mar–30 Jun 2026)

- Weekly fixed/outreach sessions per microplan

- Monthly “catch-up” rounds in low-coverage areas

- Routine supervisory visits + spot checks

- Weekly data submission and review

Phase 4 — Close-out & Handover (01–31 Jul 2026)

- Final mop-up sessions for missed groups

- Stock reconciliation + wastage review

- Final reporting package + financial close

- Lessons learned workshop + handover materials

### 8) Detailed activity plan (example table)

| Workstream | Key activities | Owner | Output | Timing |
| --- | --- | --- | --- | --- |
| Governance | Kickoff meeting, approvals, comms lines | PM | Signed kickoff MoM, approvals | Feb W1 |
| Microplanning | Mapping, targets, routes, session plans | PM + M&E + Partners | Microplan per catchment | Feb W3–W4 |
| HR & Training | Team assignment, training delivery | PM | Trained staff list, training report | Feb W4 |
| Cold chain | Equipment check, temp log setup, backup plan | Logistics | Cold-chain readiness report | Feb W2–W4 |
| Procurement | Syringes, safety boxes, PPE, fuel, printing | Logistics + Finance | Delivered supplies | Feb–Mar |
| Service delivery | Fixed/outreach/mobile sessions | Field Team Leads | Vaccination registers | Mar–Jun |
| AEFI & referral | Setup referral pathways, reporting | Clinical Lead | AEFI log + referral SOP | Feb–Jun |
| M&E & reporting | Weekly, monthly dashboards | M&E | Weekly + monthly reports | Mar–Jul |
| Accountability | Feedback channels, complaint handling | Safeguarding | Feedback log + actions | Mar–Jul |
| Close-out | Reconciliation, final report, learning | PM | Close-out package | Jul |

### 9) Deliverables (what “done” looks like)

- Approved microplans and route plans

- Cold chain readiness confirmation + contingency plan

- Training completion report and attendance logs

- Weekly service delivery reports (site-level)

- Monthly dashboard + narrative analysis

- AEFI logbook and referral documentation

- Stock reconciliation report (opening, received, used, wasted, closing)

- Final completion report (coverage, learnings, financial summary)

### 10) RACI (who does what)

| Activity | PM | Logistics | Finance | M&E | Partners | Health Authority |
| --- | --- | --- | --- | --- | --- | --- |
| Microplanning | A | C | I | R | R | C |
| Vaccine distribution | C | A/R | I | I | C | C |
| Payments & procurement | C | C | A/R | I | I | I |
| Data reporting | C | I | I | A/R | R | C |
| Supervision | A/R | C | I | C | R | C |
| Legend: R=Responsible, A=Accountable, C=Consulted, I=Informed |  |  |  |  |  |  |

### 11) Resources and logistics plan (summary)

Team structure (example)

- 1 PM, 1 Logistics Lead, 1 Finance Lead, 1 M&E Officer

- Field teams per district: vaccinator(s), recorder, crowd controller, CHW support

Transport

- Scheduled weekly deliveries from central store to facilities

- Last-mile distribution to outreach points (motorbike/4x4 depending on terrain)

Cold chain

- Temperature monitoring twice daily at fixed sites

- Ice packs / cold boxes for outreach

- Backup: alternative storage site + emergency transport contact list

### 12) Budget summary (high-level headings)

- Personnel and field allowances

- Transport & fuel

- Cold-chain equipment maintenance and consumables

- Printing & materials (registers, consent/info sheets)

- PPE and IPC supplies

- Community engagement activities

- Monitoring, supervision, and evaluations

- Contingency (e.g., 5–10%)

(Detailed budget sits in the Flood Relief Budget Plan / project budget module; this section is only a summary.)

### 13) Risk register (starter set)

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Cold chain excursion | Med | High | Temp logs, backup storage, rapid response SOP | Logistics |
| Stockouts of ancillaries | Med | High | Buffer stock, reorder trigger levels, weekly stock review | Logistics |
| Low turnout / hesitancy | Med | Med/High | CHW engagement, leader briefings, rumor tracking | PM + Partners |
| Access disruptions (weather/roads) | Med | Med | Flexible routes, preposition stock, contingency days | PM |
| Data quality issues | Med | Med | Training, weekly checks, spot audits, simple tools | M&E |
| Staff turnover/absences | Low/Med | Med | Roster backups, rapid onboarding pack | PM |
| Safety/security incidents | Low/Med | High | Context monitoring, movement protocols, escalation | PM |

### 14) Monitoring, evaluation, and reporting

Core indicators (examples)

- doses administered (by antigen/target group)

- Coverage % vs target (per catchment)

- Wastage rate % (by antigen)

- Cold chain compliance % (temp log completeness + excursions)

- outreach/mobile sessions delivered vs planned

- AEFI cases reported and resolved per protocol

- Data completeness and timeliness (weekly submissions)

Reporting cadence

- Weekly: site summary + stock snapshot + issues/escalations

- Monthly: dashboard + narrative (progress, constraints, corrective actions)

- Final: completion report + lessons learned + reconciliations

### 15) Quality assurance and safeguarding

- Follow national clinical protocols and IPC guidance

- Use standard checklists for supervision visits

- Maintain a community feedback channel (phone/box/CHW collection)

- Document and act on complaints; escalate safeguarding issues immediately

### 16) Change control (how changes are handled)

Any changes to:

- timeline (+/- 2 weeks),

- target districts,

- budget reallocations above an agreed threshold,

- delivery model (major shift),
 must be documented in a Change Request approved by PM + relevant authority/management.

### 17) Close-out plan

Close-out criteria

- All planned sessions delivered (or formally revised)

- Coverage validated and explained where gaps remain

- Stock reconciled and signed off

- Final financial reconciliation completed

- Lessons learned captured and shared

Close-out outputs

- Final report package (program + M&E + finance)

- Archived documentation (audit-ready)

- Handover notes to routine health services

### Appendix A — Microplan checklist (quick)

- Catchment list confirmed

- Target population estimates validated

- Session plan per week (fixed/outreach/mobile)

- Staff roster and training completion

- Transport plan + fuel plan

- Cold chain plan + backups

- Supplies forecast + buffer levels

- Data tools printed/loaded and tested