# Curriculum Development Plan

Project: Education for Displaced Children (EDC)
 Document Type: Curriculum Development Plan (CDP)
 Document ID: EDC-CDP-2026-01-001 (Demo)
 Version: v1.0 (Draft for review)
 Prepared by: Education Technical Unit (Demo)
 Reporting / Planning Period: 01 Feb 2026 – 31 Jul 2026
 Geographic Focus: Sundby Reception Corridor (Demo)
 Target Group: Displaced children aged 6–14 (primary and lower secondary bridging)
 Language(s) of Instruction: Host-country language + supported bilingual scaffolding (Demo)

## 1) Purpose and Scope

This Curriculum Development Plan defines the approach to designing, piloting, and rolling out a context-appropriate learning package for displaced children with varied prior schooling. The plan covers curriculum design principles, learning outcomes, materials development, teacher training, assessment, safeguarding, and a phased implementation schedule across three learning hubs.

Scope includes:

- Foundational learning (literacy, numeracy)

- Accelerated/bridging content for out-of-school learners

- Life skills, child protection, and psychosocial well-being supports

- Teacher guides, learner materials, and simple assessments

Out of scope:

- National certification arrangements (handled through education authority coordination)

- Construction of permanent school infrastructure (handled under separate facilities workstream)

## 2) Context and Needs Summary (Demo)

Displaced children arriving in the corridor have interrupted schooling, inconsistent language familiarity, and diverse learning levels within the same age groups. Barriers include mobility (short stays), documentation gaps, and limited learning materials. The program will provide a structured but flexible learning pathway that can be delivered in modular units and transferred between sites.

## 3) Curriculum Goals and Outcomes

### 3.1 Overall Goal

Ensure displaced children access safe, inclusive, and continuous learning that restores foundational skills and supports transition into formal education or stable learning pathways.

### 3.2 Outcomes (6-month horizon)

- Improved foundational skills: Most learners demonstrate measurable progress in literacy and numeracy.

- Increased learning continuity: Learners can continue modules across sites with portable records.

- Strengthened well-being and safety: Learning spaces apply safeguarding standards and integrate psychosocial support practices.

## 4) Design Principles

- Do no harm & safeguarding-first: Safe access, inclusive classroom management, clear reporting pathways.

- Modular learning: Short units (1–2 weeks each) that can stand alone and stack logically.

- Differentiation by level (not only age): Placement into Level A/B/C within age bands.

- Language-aware instruction: Visual supports, bilingual scaffolding, and gradual transition to host-language proficiency.

- Trauma-informed pedagogy: Predictable routines, positive behavior supports, and referral protocols.

- Inclusive education: Adaptations for disability, gender equity, and barriers to participation.

## 5) Curriculum Structure

### 5.1 Grade Bands and Levels

Learners are grouped into:

- Band 1 (6–9 years): Level A (emerging), Level B (developing)

- Band 2 (10–14 years): Level B (developing), Level C (bridging)

Placement: rapid learning assessment (RLA) in week 1 + teacher observation.

### 5.2 Subjects and Weekly Time Allocation (Guidance)

| Component | Band 1 (hrs/week) | Band 2 (hrs/week) | Notes |
| --- | --- | --- | --- |
| Literacy & Language | 6 | 5 | phonics/fluency + comprehension |
| Numeracy | 5 | 5 | number sense, operations, problem-solving |
| Science & Environment | 2 | 2 | practical, low-material activities |
| Social Studies / Civic Learning | 2 | 2 | community, safety, rights & responsibilities |
| Life Skills + SEL/PSS | 2 | 2 | structured SEL sessions + routines |
| Creative / Physical Activities | 3 | 3 | play-based learning & movement |
| Total | 20 | 19 | adjust based on site schedule |

### 5.3 Learning Progression (Example Modules)

Literacy (Band 1):

- Module L1: letter-sound mapping & phonemic awareness

- Module L2: decoding + high-frequency words

- Module L3: sentence building + basic comprehension

- Module L4: short stories + retell + writing basics

Numeracy (Band 2):

- Module N1: number sense (place value)

- Module N2: operations & mental math strategies

- Module N3: fractions/decimals foundations

- Module N4: measurement + word problems

## 6) Teaching and Learning Approach

- Lesson design: “I do / We do / You do” with frequent checks for understanding.

- Group work: structured pair practice; learning stations (especially for mixed-level groups).

- Low-resource methodology: activities designed for minimal materials (paper, pencils, local objects).

- Attendance flexibility: lesson plans include quick recap segments for new arrivals.

- Positive behavior support: classroom agreements, restorative routines, non-violent discipline.

## 7) Assessment Strategy

### 7.1 Tools

- Rapid Learning Assessment (RLA): short placement tool for literacy/numeracy (15–20 minutes)

- Formative checks: weekly quizzes, teacher observation rubrics

- Monthly progress checks: brief reading fluency and numeracy benchmarks

- Learner portfolio: simple work samples + skill checklist

### 7.2 Documentation

Each learner receives a portable learning card:

- learner ID (non-sensitive), level placement, module completion, teacher notes

## 8) Teacher Training and Support

### 8.1 Training Package (Initial + Ongoing)

- Initial training (3 days):

  - safeguarding & reporting, child-friendly spaces, PSEA basics

  - differentiated instruction + language scaffolding

  - assessment tools + learner records + inclusive practices

- Coaching: weekly classroom observation + feedback cycles

- Community of practice: bi-weekly 60-minute teacher circle for lesson-sharing

### 8.2 Staffing Assumptions (Demo)

- 1 education coordinator (corridor-wide)

- 1 site lead per hub

- 2–4 teachers per hub (depending on attendance)

- volunteer classroom assistants for crowd management and translation support (as available)

## 9) Materials Development

### 9.1 Deliverables

- Teacher guide (per band) with 24 weeks of lesson plans

- Learner workbooks (Band 1, Band 2)

- Flashcards + visual aids pack (printable)

- Classroom routines posters (multi-language)

### 9.2 Production Plan

- Prototype in Month 1

- Print small pilot batch for Months 2–3

- Revise and print scale batch for Months 4–6

## 10) Safeguarding, Inclusion, and Well-being

- Minimum standards at learning hubs: controlled entry, clear child pickup procedures, and incident log

- Referral pathways: mapped for protection and psychosocial services (Demo)

- Inclusion adaptations: seating arrangements, alternative formats, buddy system, quiet corners

- Gender and accessibility: separate latrine access if applicable, safe routes, participation monitoring

## 11) Implementation Timeline (6 Months)

| Month | Key Actions | Outputs |
| --- | --- | --- |
| Feb 2026 | needs validation, RLA design, draft curriculum framework | framework + draft scope/sequence |
| Mar 2026 | develop prototypes, train teachers, pilot start | pilot materials + trained staff |
| Apr 2026 | refine modules, strengthen assessment + learner records | v0.9 materials + QA checklist |
| May 2026 | scale delivery, coaching cycles, PDM-style learner feedback | midline learning snapshot |
| Jun 2026 | continued delivery, targeted remediation groups | improved progression rates |
| Jul 2026 | endline checks, curriculum revisions, close-out pack | v1.1 final package + report |

## 12) Governance and Approvals (Demo)

Curriculum Review Committee:

- Education Coordinator (Chair)

- M&E Officer

- Safeguarding Focal Point

- Site Leads (3)

- Local education authority liaison (observer)

Approval steps:

- Technical review (content + pedagogy)

- Safeguarding/inclusion review

- Operational feasibility review

- Final sign-off and version release

Sign-off

- Prepared by: ____________________ Date: __________

- Reviewed by (Education Lead): ____________________ Date: __________

- Approved by (Program Manager): ____________________ Date: __________