Food Distribution Report (ERP Demo Seed Data)
Project: Food Assistance for Refugees
Donor / Funding Code: ECHO-FAFR-2026-01 (Demo)
Implementing Org: NorthBridge Relief (Demo)
Reporting Period: 05 Jan 2026 – 11 Jan 2026
Geography: Sundby Reception Corridor (Demo region)
Warehouses: Sundby Central Warehouse (SCW-01)
Distribution Modality: In-kind (standard food basket)
Prepared by: Operations & M&E Unit (Demo)
Document ID: FAFR-FDR-2026-01-001 (Demo)

1) Executive Summary
During the reporting period, NorthBridge Relief conducted 4 distribution days across 3 distribution sites, reaching 1,170 households (5,012 individuals) with a 7-day household food basket. Overall delivery achieved 97.5% of the planned household target (1,200 HH), with minor shortfalls driven by last-minute household departures and re-verification outcomes. Stock movements were reconciled using waybills, signed distribution lists, and warehouse bin cards; total recorded losses remained below 0.5% and were attributable to minor packaging damage.

2) Objectives (Period)
1. Provide a 7-day food basket to verified refugee households in the Sundby Reception Corridor.
2. Ensure safe, dignified distributions with accessibility measures for vulnerable individuals.
3. Maintain end-to-end traceability (warehouse → transport → distribution → reconciliation).

3) Key Results (KPIs)
Targets vs. Achievements
- Planned households: 1,200
- Reached households: 1,170
- % reached: 97.5%
- Planned individuals: 5,100 (planning figure)
- Reached individuals: 5,012
- Average household size (observed): 4.28
- Distribution days: 4
- Post-Distribution Monitoring (PDM): 40 HH (phone + on-site)
- Complaints/feedback cases logged: 27 (resolved: 24; pending: 3)

4) Ration Composition (7-Day Basket)
Per household ration (standard):
- Rice: 12 kg
- Lentils: 4 kg
- Fortified blended flour (CSB+): 3 kg
- Vegetable oil: 1.8 L
- Sugar: 1 kg
- Iodized salt: 0.5 kg
Notes: Households verified on-site against the master list and issued a distribution token prior to collection.

5) Distribution Summary (Planned vs Actual Commodities)
Item	Unit	Planned Qty (1,200 HH)	Distributed Qty (1,170 HH)	Variance	Comments
Rice	kg	14,400	14,040	-360	HH reached lower than planned
Lentils	kg	4,800	4,680	-120	As above
CSB+	kg	3,600	3,510	-90	As above
Vegetable oil	L	2,160	2,106	-54	As above
Sugar	kg	1,200	1,170	-30	As above
Iodized salt	kg	600	585	-15	As above

6) Distribution Events (Sites, Dates, Outputs)
Date	Site	Site Code	Households Served	Individuals Served	Time Window	Remarks
05 Jan 2026	Sundby Hub (East Hall)	DS-01	320	1,376	09:00–14:00	Smooth flow; added elderly priority lane
07 Jan 2026	Larkfield Transit Point	DS-02	290	1,241	10:00–16:10	Weather delays; extra canopy installed
09 Jan 2026	Sundby Hub (East Hall)	DS-01	310	1,326	09:00–15:00	Peak congestion at noon; staggered tokens
11 Jan 2026	Meadowgate Reception Site	DS-03	250	1,069	10:00–15:30	Accessibility support improved (wheelchair ramp)

Total: 1,170 HH / 5,012 individuals

7) Beneficiary Profile (Registration Snapshot)
Category	Count	%
Women (18+)	1,756	35.0%
Men (18+)	1,612	32.2%
Children 0–5	612	12.2%
Children 6–17	928	18.5%
Older persons (60+)	104	2.1%
Total individuals	5,012	100%

Vulnerability markers (households):
- Female-headed households: 198
- Households including PwD: 87
- Households including elderly (60+): 64

8) Warehouse & Stock Reconciliation (SCW-01)
Stock Movement Summary (Reporting Period)
Item	Unit	Opening	Received	Distributed	Loss/Adjust	Closing
Rice	kg	3,000	12,000	14,040	60	900
Lentils	kg	1,000	4,000	4,680	20	300
CSB+	kg	500	3,500	3,510	10	480
Vegetable oil	L	300	2,000	2,106	6	188
Sugar	kg	200	1,200	1,170	0	230
Iodized salt	kg	120	600	585	5	130

Loss/Adjust notes (demo):
- Minor packaging tears observed during handling (recorded and segregated).
- All losses recorded with batch IDs and supervisor sign-off.

9) Accountability, Safeguarding, and Feedback
Community communications used
- Posters at reception centers (3 languages)
- Community briefings via leaders (2 sessions)
- Helpdesk at each site + hotline
Feedback/Complaints (27 cases) — top themes
- Queue/wait time: 11
- Household verification questions: 8
- Missing/incorrect item counts: 5
- Accessibility support: 3
Resolution status
- Resolved on-site: 18
- Resolved after verification (within 72 hrs): 6
- Pending (documentation follow-up): 3
Safeguarding measures
- Separate priority lane (elderly, PwD, pregnant/lactating)
- Crowd management volunteers trained on code of conduct
- Referral info visible at helpdesk

10) Challenges & Mitigation
- Congestion at midday peaks → introduced staggered token times (Site DS-01)
- Weather disruption at DS-02 → added canopy + extended distribution window
- New arrivals not on master list → referred to registration desk; scheduled for next cycle

11) Recommendations (Next Period)
1. Increase staffing at verification desks during peak hours (11:00–13:00).
2. Pre-position rain protection at DS-02 during winter months.
3. Expand PDM sample size to 60 HH for tighter quality checks.

12) Approvals (Demo)
Prepared by: ____________________ Date: 12 Jan 2026
Reviewed by (Ops Lead): ____________________ Date: 12 Jan 2026
Approved by (Program Manager): ____________________ Date: 13 Jan 2026