## Overview
Resource Allocation Overview — Education for Displaced Children (EDC)
Project Code | EDC-2026-01 |  |  | Planning Period | 01 Feb 2026 – 31 Jul 2026
Geographic Focus | Sundby Reception Corridor (Demo) |  |  | Target Group | Displaced children aged 6–14
Implementation Sites | 3 learning hubs (Sundby Hub, Larkfield Transit, Meadowgate) |  |  | Document ID | EDC-RAO-2026-01-001 (Demo)
Prepared By | Education Technical Unit (Demo) |  |  | Version | v1.0
Resource Snapshot
Total Planned Budget (EUR) | 628800 | Total Human Resources (FTE) | 17.7 | # Teachers (roster) | 12 | # Learning Hubs | 3
Planned Learner Capacity / month | 750 | Assessment Frequency | Monthly progress check | Materials Print Runs | 2 (pilot + scale) | Complaint Channels | Helpdesk + hotline
Allocation by Workstream (6-month plan)
Workstream | Lead Role | Planned FTE | Budget (EUR) | % of Total | Key Outputs (high-level) | Start | End
Curriculum framework & localization | Education Coordinator | 1.8 | 112000 | 17.81% | Scope/sequence; lesson prototypes; assessment tools | 2026-02-01 | 2026-04-30
Teacher training & coaching | Site Leads | 2.2 | 96000 | 15.27% | 3-day initial training; weekly coaching cycles; CoP sessions | 2026-03-01 | 2026-07-31
Learning materials production & replenishment | Logistics Officer | 1 | 145500 | 23.14% | Workbooks; flashcards; posters; classroom kits; reprints | 2026-02-15 | 2026-06-30
Learning hub delivery (site ops) | Site Leads | 10.3 | 162500 | 25.84% | Class delivery across 3 hubs; attendance & learner records | 2026-02-15 | 2026-07-31
Monitoring, evaluation & assessments | M&E Officer | 0.7 | 24000 | 3.817% | Placement checks; monthly progress benchmarks; learning snapshot | 2026-02-15 | 2026-07-31
Safeguarding, inclusion & AAP | Safeguarding Focal Point | 0.8 | 18000 | 2.863% | PSEA briefings; referral mapping; feedback mechanism & response | 2026-02-01 | 2026-07-31
Project management & overhead | Program Manager | 0.9 | 70800 | 11.26% | Coordination; finance/admin; reporting; audits; compliance | 2026-02-01 | 2026-07-31
TOTAL |  | 17.7 | 628800 | 100%
Notes (Demo): FTE values represent planned average engagement across the 6‑month period. Budget lines include goods/services and prorated staff costs. Percentages are calculated automatically.

## Staffing
Staffing & Roles Plan — EDC (Demo)
Planned staffing for implementation across three learning hubs. Costs are indicative for demo purposes.
Role | Headcount | FTE/Person | Total FTE | Start | End | Primary Location | Contract Type | Key Responsibilities
Education Coordinator | 1 | 1 | 1 | 2026-02-01 | 2026-07-31 | Corridor-wide | Fixed-term | Technical leadership; curriculum governance; coordination
Curriculum Specialist (consultant) | 1 | 0.5 | 0.5 | 2026-02-01 | 2026-04-30 | Remote + field visits | Consultancy | Module drafting; localization; teacher guide development
M&E Officer | 1 | 0.5 | 0.5 | 2026-02-15 | 2026-07-31 | Corridor-wide | Fixed-term | Assessments; data QA; monthly learning snapshots
Safeguarding Focal Point | 1 | 0.3 | 0.3 | 2026-02-01 | 2026-07-31 | Corridor-wide | Fixed-term | Safeguarding/PSEA; referrals; staff briefings
Logistics Officer | 1 | 0.5 | 0.5 | 2026-02-01 | 2026-07-31 | Sundby | Fixed-term | Printing/warehousing; hub supplies; distribution to sites
Finance/Admin Officer | 1 | 0.5 | 0.5 | 2026-02-01 | 2026-07-31 | Sundby | Fixed-term | Payments; procurement admin; reporting support
Site Lead (per hub) | 3 | 0.8 | 2.4 | 2026-02-15 | 2026-07-31 | 3 hubs | Fixed-term | Daily hub ops; teacher support; attendance & learner records
Teachers (roster) | 12 | 0.75 | 9 | 2026-02-15 | 2026-07-31 | 3 hubs | Stipend | Deliver lessons; manage classrooms; learner progress tracking
Classroom Assistants (stipended) | 6 | 0.5 | 3 | 2026-02-15 | 2026-07-31 | 3 hubs | Stipend | Translation support; classroom set-up; learner support
TOTAL | 27 |  | 17.7

## Budget
Budget Allocation Summary — EDC (Demo)
High-level budget by category. Percentages and totals calculate automatically.
Category | Description | Amount (EUR) | % of Total | Owner | Procurement Method | Timing | Notes
Personnel (core staff) | Coordinator, M&E, safeguarding, logistics, finance/admin (prorated) | 214800 | 34.16% | Program Manager | N/A (HR) | Feb–Jul | Contracts aligned to project duration
Curriculum consultants | Specialist drafting, localization, editing, design support | 72000 | 11.45% | Education Coordinator | RFQ / framework | Feb–Apr | Deliverables-based payments
Learning materials (print/kits) | Workbooks, flashcards, posters, classroom kits, reprints | 115500 | 18.37% | Logistics Officer | Competitive RFQ | Feb–Jun | Pilot + scale print runs
Teacher training & coaching | Training venue, per diem, materials, coaching travel | 48000 | 7.634% | Site Leads | Direct purchase / RFQ | Mar–Jul | 3-day ToT + ongoing coaching
Learning hub supplies | Stationery, whiteboards, basic learning aids, minor repairs | 52500 | 8.349% | Site Leads | Petty cash / local procurement | Feb–Jul | Monthly replenishment
Transport & logistics | Warehouse-to-hub deliveries, fuel, loading/unloading | 36000 | 5.725% | Logistics Officer | Service contract | Feb–Jul | Fixed schedule + ad-hoc runs
MEL (assessments/PDM) | Assessment tools, enumerators, phone credit, QA checks | 24000 | 3.817% | M&E Officer | Direct purchase / RFQ | Feb–Jul | Monthly progress checks
Safeguarding & AAP | Helpdesk setup, signage, training, hotline fees | 18000 | 2.863% | Safeguarding Focal Point | Direct purchase | Feb–Jul | Complaint response tracked
Admin/Overhead | Shared services, compliance, audit support (approx. 5%) | 48000 | 7.634% | Finance/Admin | N/A | Feb–Jul | Calculated as policy rate
TOTAL | Total requested / planned | 628800 | 100%

## Monthly Plan
Monthly Resource Plan (Feb–Jul 2026) — EDC (Demo)
Planned intensity and key deliverables by month. Use this as an overview for scheduling and procurement.
Workstream / Input | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Key Deliverable by End of Period
Curriculum framework & localization | High | High | Med | Low | Low | Low | Curriculum v1.1 + teacher guides ready
Teacher training (initial) | Low | High | Med | Low | Low | Low | All teachers trained + refresher plan
Coaching & communities of practice | Low | Med | High | High | High | High | Weekly coaching cycles documented
Materials: pilot print + kit assembly | High | High | Med | Low | Low | Low | Pilot materials deployed in 3 hubs
Materials: scale print + replenishment | Low | Med | High | High | High | Med | Scale batch delivered + reprint buffer
Learning hub operations (class delivery) | Med | High | High | High | High | High | Routine delivery stabilized
MEL: placement + monthly benchmarks | Med | Med | Med | Med | Med | Med | Monthly progress snapshot compiled
Safeguarding & AAP (helpdesk/hotline) | Med | Med | Med | Med | Med | Med | Feedback loop operational; issues tracked
Procurement & logistics (transport, storage) | High | High | Med | Med | Med | Low | Supply chain stabilized; lead times reduced
Legend: High = major activity / heavy resource use; Med = steady resourcing; Low = limited activity / maintenance.