## INDEX
Relief Projects — Seed Documents (Google Sheets style)
This workbook contains three example documents used for training/demo data. You can edit any blue fields later.
Project | Vaccination Drive in Rural Africa
Prepared | 2026-01-11
Notes | These are realistic-but-fake examples. Replace with real values before operational use.
Contents
Document | What it's for | Last updated | Open
Vaccination Rollout Strategy | Operational plan: target groups, timeline, roles, risks, KPIs. | 2026-01-11 | Go
Vaccine Inventory Report | Stock tracking: batches, expiry, on-hand, consumption, alerts, summary charts. | 2026-01-11 | Go
Flood Relief Budget Plan | Budget worksheet: cost lines, assumptions, category totals, summary chart. | 2026-01-11 | Go

## Vaccination Strategy
Vaccination Rollout Strategy — Vaccination Drive in Rural Africa
Realistic example document (seed data). Replace names, dates, and numbers with real information before use.
1) Overview
Purpose | Deliver a safe, equitable vaccination rollout across rural communities by combining fixed-site clinics and mobile outreach.
Primary geography | Kijiji District (rural, dispersed villages; limited cold-chain capacity at peripheral sites).
Time window | 12-week rollout (includes setup, rollout waves, and catch-up days).
Target disease | Routine immunization + catch-up campaign (example).
Key partners | District Health Office; community leaders; implementing partner NGOs; cold-chain logistics provider.
2) Target groups & dose planning
Target group | Estimated population | Coverage target | Doses per person | Estimated doses needed | Delivery approach | Notes | Owner
Children 0–5 | 18200 | 90% | 1 | 16380 | Fixed + outreach | Prioritize remote villages for outreach days. | EPI Lead
Pregnant women | 4200 | 85% | 1 | 3570 | ANC clinics | Align with antenatal visit schedules. | Maternal Health
Health workers | 860 | 95% | 1 | 817 | Facility-based | Include private clinics in roster. | HR Officer
Adults 60+ | 5200 | 80% | 1 | 4160 | Mobile outreach | Use community mobilizers for attendance. | Community Lead
TOTAL |  |  |  | 24927
3) Rollout timeline (12 weeks)
Week | Dates (example) | Focus | Key activities | Deliverable | Owner | Dependencies | Status (example)
1 | 2026-01-18 to 2026-01-24 | Setup | Confirm microplan, map sites, validate target estimates, finalize cold-chain routes. | Microplan + site schedule approved | District Team | Cold chain + mobilization | On track
2 | 2026-01-25 to 2026-01-31 | Setup | Staff briefing, community engagement launch, stock pre-positioning. | Teams trained; initial stock at hub | District Team | Cold chain + mobilization | On track
3 | 2026-02-01 to 2026-02-07 | Wave 1 | Fixed-site vaccination + outreach to nearest clusters; daily reconciliation. | Weekly coverage report | District Team | Cold chain + mobilization | On track
4 | 2026-02-08 to 2026-02-14 | Wave 1 | Fixed-site vaccination + outreach to nearest clusters; daily reconciliation. | Weekly coverage report | District Team | Cold chain + mobilization | On track
5 | 2026-02-15 to 2026-02-21 | Wave 1 | Fixed-site vaccination + outreach to nearest clusters; daily reconciliation. | Weekly coverage report | District Team | Cold chain + mobilization | On track
6 | 2026-02-22 to 2026-02-28 | Wave 2 | Outreach to remote villages; catch-up for missed target groups. | Outreach log + coverage update | District Team | Cold chain + mobilization | On track
7 | 2026-03-01 to 2026-03-07 | Wave 2 | Outreach to remote villages; catch-up for missed target groups. | Outreach log + coverage update | District Team | Cold chain + mobilization | On track
8 | 2026-03-08 to 2026-03-14 | Wave 2 | Outreach to remote villages; catch-up for missed target groups. | Outreach log + coverage update | District Team | Cold chain + mobilization | On track
9 | 2026-03-15 to 2026-03-21 | Wave 3 | Second pass: low-coverage areas, high-risk groups; stock rebalancing. | Exception list cleared | District Team | Cold chain + mobilization | On track
10 | 2026-03-22 to 2026-03-28 | Wave 3 | Second pass: low-coverage areas, high-risk groups; stock rebalancing. | Exception list cleared | District Team | Cold chain + mobilization | On track
11 | 2026-03-29 to 2026-04-04 | Closeout | Catch-up days, inventory close, final reporting and lessons learned. | Final campaign report | District Team | Cold chain + mobilization | On track
12 | 2026-04-05 to 2026-04-11 | Closeout | Catch-up days, inventory close, final reporting and lessons learned. | Final campaign report | District Team | Cold chain + mobilization | On track
4) Roles & responsibilities
EPI Lead | 1 | Overall coordination, daily review, liaison with district. | District HQ | Coverage dashboard; microplan | Deputy EPI | Approves schedule changes. | Health Dept
Cold-chain Technician | 2 | Storage checks, temperature logs, ice-pack prep, route QA. | Hub + routes | Temp loggers; fridge tags | Senior Tech | Daily cold chain report. | Logistics
Vaccination Team | 12 | Administer vaccines, record doses, adverse event watch. | Sites/outreach | Registers; PPE | Reserve team | 4 teams × 3 staff. | Field Ops
Community Mobilizers | 18 | Community sensitization, appointment reminders, escort support. | Villages | Megaphones; SMS lists | Lead mobilizer | Coordinate with leaders. | Community Lead
5) Monitoring indicators (KPIs)
Coverage rate | Doses administered / target population (per group). | >= 85% | Daily register + weekly roll-up | Weekly | M&E | Report by village/ward. | On track
Cold chain compliance | % days with temp in range at hub + sites. | >= 95% | Temp logs | Daily | Logistics | Escalate deviations within 2h. | On track
Wastage rate | Wasted doses / doses issued. | <= 5% | Stock cards + session tally | Weekly | EPI Lead | Investigate spikes. | Watch
AEFI reporting | # AEFI reports logged within 24h. | 100% within 24h | AEFI form log | Daily | Clinical Lead | Zero is ok if none occurred. | On track
6) Risks & mitigation
Cold-chain failure at peripheral site | Medium | High | Temp excursions; power outages | Use ice-lined coolers; daily temp checks; move stock to hub if unstable. | Cold-chain Tech | District Logistics | Prioritize solar sites.
Low turnout in remote villages | Medium | Medium | Low mobilizer reports; missed appointments | Increase mobilization; coordinate with leaders; add catch-up days. | Community Lead | District Health Officer | Use radio + local gatherings.
Stock-out of syringes/safety boxes | Low | High | Reorder point triggered; delayed deliveries | Maintain buffer stock; weekly procurement check; alternative supplier list. | Procurement | Ops Manager | Track lead times.
Misinformation / rumors | Medium | Medium | Social chatter; refusal spikes | Rapid response messaging; trusted spokespersons; hotline. | Comms | Program Director | Document incidents.
Back to INDEX

## Inventory Report
Vaccine Inventory Report — Vaccination Drive in Rural Africa
Example stock report (seed data). Uses formulas for on-hand and alerts.
Reporting period (days) | 7 |  | Report date | 2026-01-11
1) Stock by site (batches)
Kijiji Hub Store | Measles-Rubella | MR-24-018 | 2026-05-31 | 5200 | 1200 | 950 | 20 | 0 | 5430 | 135.7143 | 40.0105
Kijiji Hub Store | Pentavalent | PEN-24-122 | 2026-08-09 | 4100 | 800 | 720 | 18 | -10 | 4152 | 102.8571 | 40.3667
Nuru Clinic | Measles-Rubella | MR-24-021 | 2026-03-07 | 850 | 300 | 260 | 8 | 0 | 882 | 37.1429 | 23.7462
Nuru Clinic | Oral Polio | OPV-24-077 | 2026-04-11 | 1200 | 0 | 310 | 6 | 0 | 884 | 44.2857 | 19.9613
Maji Clinic | Pentavalent | PEN-24-130 | 2026-02-15 | 620 | 200 | 260 | 7 | 0 | 553 | 37.1429 | 14.8885
Ziwa Outreach Team | Td (Tetanus/Diphtheria) | TD-24-044 | 2026-06-20 | 400 | 250 | 180 | 4 | 0 | 466 | 25.7143 | 18.1222
2) Summary (on-hand by vaccine)
Vaccine | Total on-hand | % of total
Measles-Rubella | 6312 | 51.04%
Oral Polio | 884 | 7.148%
Pentavalent | 4705 | 38.04%
Td (Tetanus/Diphtheria) | 466 | 3.768%
TOTAL | 12367 | 100%
3) Alerts (near expiry & low stock)
Note: rows highlight automatically. Use this section to filter and act (redistribute stock, prioritize use, or request replenishment).
Back to INDEX

## Flood Budget
Flood Relief Budget Plan — Example (Seed Data)
Example budget for a rapid flood response package. Replace quantities and rates with real procurement quotes.
Base currency | USD |  | Contingency % | 8% |  | Prepared | 2026-01-11
Exchange rates (for reporting) |  |  |  | USD→EUR | 0.92 | USD→SEK | 10.4 | USD→GBP | 0.79
1) Budget lines
Shelter | Emergency shelter kits (tarps + rope) | kit | 1500 | 22.5 | 33750 | 2700 | 36450 | 33534 | 379080
WASH | Water purification tablets (10k tabs) | pack | 220 | 18 | 3960 | 316.8 | 4276.8 | 3934.656 | 44478.72
WASH | Jerry cans (20L) | unit | 3000 | 6.4 | 19200 | 1536 | 20736 | 19077.12 | 215654.4
Health | First aid kits | kit | 450 | 28 | 12600 | 1008 | 13608 | 12519.36 | 141523.2
Logistics | Truck rental (4x4) — 2 weeks | truck-week | 8 | 780 | 6240 | 499.2 | 6739.2 | 6200.064 | 70087.68
Logistics | Fuel & transport allowance | lump-sum | 1 | 5200 | 5200 | 416 | 5616 | 5166.72 | 58406.4
Staffing | Field team per diem (12 staff × 14 days) | day | 168 | 35 | 5880 | 470.4 | 6350.4 | 5842.368 | 66044.16
Comms | Community radio announcements | spot | 80 | 12 | 960 | 76.8 | 1036.8 | 953.856 | 10782.72
TOTAL |  |  |  |  | 87790 | 7023.2 | 94813.2 | 87228.144 | 986057.28
2) Summary by category
Comms | 1036.8 | 1.094%
Health | 13608 | 14.35%
Logistics | 12355.2 | 13.03%
Shelter | 36450 | 38.44%
Staffing | 6350.4 | 6.698%
WASH | 25012.8 | 26.38%
Back to INDEX